## Slide 1
CONSTRUCTION SCHEDULE
Client:
Mr. John Doe
FINISH BY MAY 21, 2026
Planning & Permits
Site Preparation
Foundation Work
Framing & Roofing
MEP
Insulation
Drywall & Interior Prep
Final Inspections
Finalize layout
Sign contract
Schedule inspections
Clear and grade the land
Mark foundation layout
Schedule inspections
Excavate and pour footings
Install rebar and forms
Apply waterproofing
Frame walls
Install roof trusses
Sheathing roof
HVAC rough-in
Rough electrical wiring
Set main electrical panel
Install wall & attic insulation
Seal air gaps
Prepare for drywall
Hang and tape drywall
Sand and smooth surfaces
Prime walls for painting
Pass final inspections
Deliver keys & documents
W1
W2
W3
W4
W5
W6
W7
W8
W9
W10
Close permits